## Slide 1: Work Plans
420-E31 Systems III

## Slide 2: Developing Work Plans
A work plan, is a dynamic schedule that records and keeps track of all tasks to be accomplished over the course of the project
Created after a project manager has a general idea of the project’s size and rough schedule
The work plan is usually the main item in a project management software application, e.g. Microsoft Project

## Slide 3: Developing a Work Plan
Identify tasks in the project
Estimate task length
Determine task dependencies
Assign resources to tasks

## Slide 4: Example of a Work Plan Task
Work Plan Information Example
Name of task Perform economic feasibility
Start date Jan 05, 2014
Completion date Jan 19, 2014
Person assigned Mary Smith, sponsor
Deliverable(s) Cost-benefit analysis
Completion status Open
Priority High
Resources needed Spreadsheet
Estimated time 16 hours
Actual time 14.5 hours
Notes: This is the basic information. Most s/w packages allow a lot of other things.
What are some important things that are missing?
Cost (estimated and actual)
Planned vs. actual
Last update

## Slide 5: How to Identify Tasks
Top-down approach
  Identify highest level tasks as phases in the project
  Break them into increasingly smaller units
Methodology
  Using standard list of tasks
  Similar previous projects
Work Breakdown Structure (WBS)
  Hierarchical structure used to organize tasks for reporting schedules and tracking costs
Notes: Standard lists from PMI and other places
Similar projects is just experience

## Slide 6: How to use Work Breakdown Structure (WBS)
Specify high level tasks
Break down each step into smaller tasks and number them in a hierarchical fashion
WBS can be done in two ways
  SDLC phase
  Product
Notes: Start with phases: Inception, Elaboration, Construction, Transition or maybe Planning, Analysis, Design & Implementation
Develop a website: One thing that happens during Inception is Feasibility Analysis
Broken down further to Technical, Economic, Organizational (Operational here)
Organizational broken down to Political & Functional
Could break it down by product/deliverable
Applets, Servers, public pages, client pages, etc.
Servers – database and application

## Slide 7: Work Breakdown Structure Example

## Slide 8: WBS Problems
They tend to be specific to the design of the information system being developed.
Too many levels of detail too early on in the SDLC for large projects or too few for small projects.
Since they are project specific, they are difficult to compare across projects.

## Slide 9: Evolutionary WBS
Organize in a standard manner across all projects (workﬂows, phases, then specific tasks)
Create in an iterative and incremental manner
  First evolutionary WBS done with initial aspects of the project, high level items
  Later on more details are added to the WBS, low level items
Comparable to earlier projects based on cost and schedule estimation
Notes: Becoming most common way of doing things
Use RUP workflows as primary areas of breakdown

## Slide 10: Managing WBS: Project Work Plan
Mechanism used to manage the tasks in the WBS
Check to see if ahead or behind schedule, changes needed
Table that lists all the WBS tasks, people assigned, variances, dependencies
Identify milestones
Notes: Go back to example and show the dependencies between tasks

## Slide 11: Tools & Techniques
Gantt Chart
  Developed by Henry Gantt in 1917
  A horizontal bar chart used to depict project tasks against a calendar
PERT Chart
  Project Evaluation & Review Technique
  A graphical network model used to depict the interdependencies between a project’s tasks

## Slide 12: Gantt Chart
Tasks listed in rows
Time listed in columns
  Can be rolled up into any increment depending on audience
Draw horizontal bars to represent duration of each task
Fill in bars as tasks are worked on
Link task dependencies by drawing an arrow between them

## Slide 13: Gantt Chart

## Slide 14: MS Project Gantt Chart
Notes: Common notations
1 – summary tasks – tasks that are further decomposed into other tasks
2 – critical tasks (red) – delay to these tasks delays whole project
3 – not critical (blue) – have slack time
4 – arrows indicate pre-requisites
5 – milestones (diamonds)

## Slide 15: PERT Charts
Another graphical representation
Lay out tasks like a flowchart
Identify task information in box
Draw lines to show dependencies
Allows easier visualization of tasks on a critical path – tasks that must be completed on time in order for project to finish on time

## Slide 16: PERT Chart Example

## Slide 17: MS Project PERT Chart
Notes: Which one is better, PERT or Gantt chart?
PERT – show dependencies very well; used for Critical Path Method that we will get to later
Gantt – More practical, more information and more time relative (no time in PERT Chart)
One benefit to using software is that it will allow you to switch views

## Slide 18: Which is Better, PERT or Gantt Chart?
PERT – show dependencies very well; used for Critical Path Method that we will get to later
Gantt – More practical, more information and more time relative (no time in PERT Chart)

## Slide 19: Tasks: Adding and defining
Top-Down approach
  Start a highest level
  Systematically develop increasing level of detail
Bottom-Up approach
  Start at lowest level task
  Aggregate into summaries and higher levels
No one best way, but experienced PM’s generally use Top-Down
Notes: Why use top down?

## Slide 20: Types of Tasks
Summary Tasks
  Grouping of tasks within a logical structure
  Nouns, e.g. Inception Phase, Detailed Design
Detail Tasks
  Any task that is not further broken down; also called Primitive Tasks
  Use present tense to indicate action, e.g. develop prototype

## Slide 21: Project Scheduling in MS Project
Three Scheduling Techniques:
Scheduling Formula
  Duration = Work ÷ Resource Units
  Can control which value has the most influence on schedule
Task Types
  Settings for tasks to control the way they are affected by the formula
Effort-driven scheduling
  Takes effect when you add resources or remove resources from tasks

## Slide 22: Project Scheduling in MS Project
Scheduling Formula
Duration
  Elapsed time a task will take, usually measured in days
  E.g. Two days to test a system
Work
  Total number of hours to complete a task
  E.g. Completing a system test takes 8 hours
Resource Unit
  Number of resources and/or percentage time that is assigned to a task
  E.g. Tester will devote 50% of time to system test.

## Slide 23: Project Scheduling in MS Project
Scheduling Formula Example
Duration = Work ÷ Resource Units
Example:
  Duration (16 hours or 2 days) =
  Work (8 hours of effort) ÷
  Resource Units (0.5 of a person’s time)

## Slide 24: Task Types in Microsoft Project
Fixed Unit Task (default)
  A task in which the assigned unit is a fixed value.
  Resource assignment units in Project are expressed either in percentages or decimals. At 100% units, a resource is working full-time; at 50% units, the resource is working half-time, and so on.

## Slide 25: Task Types in Microsoft Project
Fixed Unit Task Example
  You assign 1 painter full-time (100%) to paint walls in 4 days (the duration). The work (the time it will take the painter to complete the task at 100% effort) is 32 hours, or 4 days.
  If you increase the amount of work to 40 hours, Project recalculates the duration as 5 days. Now the painter has an extra day of work on the task.

## Slide 26: Task Types in Microsoft Project

## Slide 27: Task Types in Microsoft Project
Fixed Duration Task
  The duration for a task remains the same regardless of the number of resources assigned to it.
  Estimate how many days you have to complete the task and calculate the others based on this number.

## Slide 28: Task Types in Microsoft Project
Fixed Duration Task Example
  Your painter is assigned full-time (100%) to paint a room in 4 days. The work is 32 hours.
  Then you assign the same painter another room to paint, but he has another job in 4 days, so the painter can only work part-time (50%) painting the room.
  When you enter 50%, Project keeps the duration fixed at 4 days, and recalculates work to be 16 hours.

## Slide 29: Task Types in Microsoft Project

## Slide 30: Task Types in Microsoft Project
Fixed Work Task
  The amount of work is a fixed value.
  Changes to the task duration or the number of assigned units (or resources) don’t impact the work.
  Estimate time for task and then add the number of resources; duration is calculated.

## Slide 31: Task Types in Microsoft Project
Fixed Work Task Example
  Two painters are assigned full-time (100%) to paint the walls in 2 days (work equals 32 hours or 16 hours per painter).
  If you increase the duration of the task from 2 days to 4 days, Project sets each painter's assignment units to 50% so that each painter works only half-time and work remains constant at 32 hours.

## Slide 32: Task Types in Microsoft Project

## Slide 33: Effort-Driven Scheduling
Effort-driven (default)
  Duration of a task shortens or lengthens as resources are added or removed, while amount of effort necessary remains unchanged.
  “Keep the work constant”
Not effort driven
  Duration of task will remain the same

## Slide 34: Special Tasks
Milestones
  Important dates in schedule with a significant event occurring
  Have 0 duration; it is an event or a point in time
  Name as <deliverable><past tense> e.g. module complete, other words: delivered, accepted, done, shipped, finished

## Slide 35: Timeboxing
Allocates a fixed time period, called a time box
  Make deadline possible
  Set by development group
Reduced functionality as necessary
Fewer “finishing touches”
Geared to RAD and Agile development
Notes: Follows 80/20 rule (20% of the functionality used 80% of the time)
80% of the system can be provided in 20% of the time

## Slide 36: Timeboxing Steps
1. Set the date for system delivery.
2. Prioritize the functionality that needs to be included in the system.
3. Build the core of the system (the functionality ranked as most important).
4. Postpone functionality that cannot be provided within the time frame.
5. Deliver the system with core functionality.
6. Repeat steps 3 through 5, to add refinements and enhancements.