## Function Point Method
Description | Complexity
| Total Number | Low |  | Medium |  | High |  | Total
|  | # | Factor | # | Factor | # | Factor
Inputs | 6 | 3 | 3 | 2 | 4 | 1 | 6 | 23
Outputs | 0 |  | 4 |  | 5 |  | 7 | 0
Queries | 0 |  | 3 |  | 4 |  | 6 | 0
Files | 0 |  | 7 |  | 10 |  | 15 | 0
Program Interfaces | 0 |  | 5 |  | 7 |  | 10 | 0
Total Unadjusted Function Points (TUFP): | [7 empty] | 23
Overall System Processing Complexity
Data communications
Heavy Use Configuration
Transaction Rate
End-user efficiency
Complex Processing
Installation Ease
Multiple Sites
Performance
Distributed Functions
Online Data Entry
Online Update
Reusability
Operational Ease
Extensibility
Total Processing Complexity (PC) | 0
(0 = no effect on processing complexity; 3 = great effect on processing complexity)
Adjusted Processing Complexity (APC) | 0.65
(0.65 + 0.01 x PC)
Total Adjusted Function Points (TAFP) | 14.95
APC x TUFP
Language | LOC/FP
Ada | 154
ASP | 69
C | 148
C# | 59
COBOL | 73
Excel | 47
HTML | 43
Java | 60
JavaScript | 56
JSP | 59
PL/SQL | 46
SQL | 39
Visual Basic | 50
Total Lines of Code | 882.05
TAFP x LOC/FP for language chosen
CoCoMo Effort Calculation | 1.2349
1.4 x (LOC/1,000)
Project Time Required | 3.2186
Factor x Effort 1/3
Factor | 3

## Use Case Method
Unadjusted Actor Weighting Table
Actor Type | Description | WeightingFactor | Number | Result
Simple | External System with well-defined API | 1 |  | 0
Average | External System using a protocol-based interface, e.g., HTTP, TCT/IP, or a database | 2 |  | 0
Complex | Human | 3 |  | 0
Unadjusted Actor Weight Total (UAW) |  |  |  | 0
Unadjusted Use Case Weighting Table
Use Case Type | Description | Weighting Factor | Number | Result
Simple | 1 – 3 transactions | 5 |  | 0
Average | 4 – 7 transactions | 10 |  | 0
Complex | > 7 transactions | 15 |  | 0
Unadjusted Use Case Weight Total (UUCW) |  |  |  | 0
Unadjusted Use Case Points (UUCP) = UAW + UUCW |  |  |  | 0
Technical Complexity Factors
Factor Number | Description | Weight | Assigned Value (0 – 5) | Weighted Value
T1 | Distributed system | 2 |  | 0
T2 | Response time or throughput performance objectives | 1 |  | 0
T3 | End-user online efficiency | 1 |  | 0
T4 | Complex internal processing | 1 |  | 0
T5 | Reusability of code | 1 |  | 0
T6 | Easy to install | 0.5 |  | 0
T7 | Ease of use | 0.5 |  | 0
T8 | Portability | 2 |  | 0
T9 | Ease of change | 1 |  | 0
T10 | Concurrency | 1 |  | 0
T11 | Special security objectives included | 1 |  | 0
T12 | Direct access for third parties | 1 |  | 0
T13 | Special User training required | 1 |  | 0
Technical Factor Value (TFactor) |  |  |  | 0
Technical Complexity Factor (TCF) = 0.6 + (0.01 * TFactor) |  |  |  | 0.6
Environmental Factors
Factor Number | Description | Weight | Assigned Value (0 – 5) | Weighted Value
E1 | Familiarity with system development process being used | 1.5 |  | 0
E2 | Application experience | 0.5 |  | 0
E3 | Object-oriented experience | 1 |  | 0
E4 | Lead analyst capability | 0.5 |  | 0
E5 | Motivation | 1 |  | 0
E6 | Requirements stability | 2 |  | 0
E7 | Part time staff | -1 |  | 0
E8 | Difficulty of programming language | -1 |  | 0
Environmental Factor Value (EFactor) |  |  |  | 0
Environmental Factor (EF) = 1.4 + (-0.03 * EFactor) |  |  |  | 1.4
Adjusted Use Case Points (UCP) = UUCP * TCF * ECF |  |  |  | 0
Calculate Person Hours Multiplier |  |  |  | 20
if sum of (# of Efactors E1 - E6 assigned value < 3)
and (# of Efactors E7-E8 assigned values > 3)
<=2 Then PHM = 20
Else If sum of (# of Efactors E1 - E6 assigned value < 3)
and (# of Efactors E7-E8 assigned values > 3)
=3 or 4 Then PHM = 28
Else Rethink Project as risk of Failure is too high
Effort in Person Hours = UCP * PHM |  |  |  | 0