## Function Point Method
Description | Complexity
| Total Number | Low |  | Medium |  | High |  | Total
|  | # | Factor | # | Factor | # | Factor |  | Function Point List
Inputs | 4 | 2 | 3 | 2 | 4 |  | 6 | 14 | companies who have requested systems, interview rooms, interviews schedules, interview results
Outputs | 5 | 3 | 4 | 1 | 5 | 1 | 7 | 24 | company contact list, interview schedule, list of interview rooms, thank you letters
Queries | 3 |  | 3 | 3 | 4 |  | 6 | 12 | number of interviews per employer, number of successful interviews, number of no shows
Files | 0 |  | 7 |  | 10 |  | 15 | 0
Program Interfaces | 0 |  | 5 |  | 7 |  | 10 | 0
Total Unadjusted Function Points (TUFP): | [7 empty] | 50
Overall System Processing Complexity
Data communications | 2
Heavy Use Configuration | 2
Transaction Rate | 1
End-user efficiency | 3
Complex Processing | 2
Installation Ease | 2
Multiple Sites | 1
Performance | 1
Distributed Functions | 1
Online Data Entry | 3
Online Update | 3
Reusability | 2
Operational Ease | 1
Extensibility | 1
Total Processing Complexity (PC) | 25
(0 = no effect on processing complexity; 3 = great effect on processing complexity)
Adjusted Processing Complexity (APC) | 0.9
(0.65 + 0.01 x PC)
Total Adjusted Function Points (TAFP) | 45
APC x TUFP
Language | LOC/FP
Ada | 154
ASP | 69
C | 148
C# | 59
COBOL | 73
Excel | 47
HTML | 43
Java | 60
JavaScript | 56
JSP | 59
PL/SQL | 46
SQL | 39
Visual Basic | 50
|  | Visual Basic | ASP | C# | Java
Total Lines of Code | 2655 | 2250 | 3105 | 2655 | 2700
TAFP x LOC/FP for language chosen
CoCoMo Effort Calculation | 3.717 | 3.15 | 4.347 | 3.717 | 3.78
1.4 x (LOC/1,000)
Project Time Required | 4.6471 | 4.3977 | 4.8961 | 4.6471 | 4.6732
Factor x Effort 1/3
Factor | 3

## Use Case Method
Unadjusted Actor Weighting Table
Actor Type | Description | WeightingFactor | Number | Result | Actor List
Simple | External System with well-defined API | 1 | 1 | 1
Average | External System using a protocol-based interface, e.g., HTTP, TCT/IP, or a database | 2 |  | 0
Complex | Human | 3 | 3 | 8
Unadjusted Actor Weight Total (UAW) |  |  |  | 9
Unadjusted Use Case Weighting Table
Use Case Type | Description | Weighting Factor | Number | Result | Use Case List
Simple | 1 – 3 transactions | 5 | 3 | 15
Average | 4 – 7 transactions | 10 | 1 | 10
Complex | > 7 transactions | 15 | 2 | 30
Unadjusted Use Case Weight Total (UUCW) |  |  |  | 55
Unadjusted Use Case Points (UUCP) = UAW + UUCW |  |  |  | 64
Technical Complexity Factors
Factor Number | Description | Weight | Assigned Value (0 – 5) | Weighted Value
T1 | Distributed system | 2 | 2 | 4
T2 | Response time or throughput performance objectives | 1 | 2 | 2
T3 | End-user online efficiency | 1 | 5 | 5
T4 | Complex internal processing | 1 | 3 | 3
T5 | Reusability of code | 1 | 3 | 3
T6 | Easy to install | 0.5 | 1 | 0.5
T7 | Ease of use | 0.5 | 5 | 2.5
T8 | Portability | 2 | 3 | 6
T9 | Ease of change | 1 | 4 | 4
T10 | Concurrency | 1 | 4 | 4
T11 | Special security objectives included | 1 | 3 | 3
T12 | Direct access for third parties | 1 | 3 | 3
T13 | Special User training required | 1 | 2 | 2
Technical Factor Value (TFactor) |  |  |  | 42
Technical Complexity Factor (TCF) = 0.6 + (0.01 * TFactor) |  |  |  | 1.02
Environmental Factors
Factor Number | Description | Weight | Assigned Value (0 – 5) | Weighted Value
E1 | Familiarity with system development process being used | 1.5 | 0 | 0
E2 | Application experience | 0.5 | 4 | 2
E3 | Object-oriented experience | 1 | 3 | 3
E4 | Lead analyst capability | 0.5 | 5 | 2.5
E5 | Motivation | 1 | 5 | 5
E6 | Requirements stability | 2 | 4 | 8
E7 | Part time staff | -1 | 5 | -5
E8 | Difficulty of programming language | -1 | 5 | -5
Environmental Factor Value (EFactor) |  |  |  | 10.5
Environmental Factor (EF) = 1.4 + (-0.03 * EFactor) |  |  |  | 1.085
Adjusted Use Case Points (UCP) = UUCP * TCF * ECF |  |  |  | 70.8288
Calculate Person Hours Multiplier |  |  |  | 28
if sum of (# of Efactors E1 - E6 assigned value < 3)
and (# of Efactors E7-E8 assigned values > 3)
<=2 Then PHM = 20
Else If sum of (# of Efactors E1 - E6 assigned value < 3)
and (# of Efactors E7-E8 assigned values > 3)
=3 or 4 Then PHM = 28
Else Rethink Project as risk of Failure is too high
Effort in Person Hours = UCP * PHM |  |  |  | 1983.2064

## PERT Analysis
Task | Optimistic | Pessimistic | Expected | Most Likely
| Duration | Duration | Duration | Duration
A | 3 | 6 | 4 | 4.1667
B | 1 | 3 | 2 | 2
C | 4 | 7 | 6 | 5.8333
D | 2 | 5 | 3 | 3.1667
E | 3 | 9 | 6 | 6
F | 3 | 13 | 4 | 5.3333
G | 4 | 11 | 7 | 7.1667
H | 12 | 30 | 21 | 21
I | 8 | 15 | 12 | 11.8333
J | 3 | 5 | 4 | 4